## Read me
MedSim VRAI — Field Test Matrix
How to run | Work the 'Test Matrix' sheet area by area. Set Result (Pass / Fail / Blocked / Not run / N-A), initials, date, Notes. Leave NO P1 row 'Not run' before sign-off.
Priorities | P1 must pass before broader rollout · P2 important · P3 edge. The Device(s) column shows the hardware each test needs.
When a test fails | Add a row to 'Issue Log': Title, Steps to reproduce, Expected, Actual, Environment, Severity, link the Test ID, Status = New.
➜ Feeding issues to Claude | The Issue Log columns are ORDERED to give Claude full context. To get a fix: filter Status = New, copy the rows (incl. header), paste into Claude Code with 'Fix these field-test issues:' + paste. Claude triages, fixes, gates, and replies with the commit; set Status Fixed → Verified after you retest.
Coverage | The 'Coverage' sheet rolls up Pass/Fail per area (live formulas) so gaps are visible. 'Environment' tracks the tablets/OS/browsers used.
Pre-flight | Run scripts/preflight.sh (6/6) before any tablet session. Area A (network/cert) gates everything else.
Status at generation | FR-008 staged errors: the arm→missed→debrief arc is already field-validated (test H11). Everything else awaits this matrix.

## Test Matrix
Test ID | Area | Pri | Test case | Preconditions | Steps | Expected result | Device(s) | Result | Tester | Date | Notes
A · Network & pairing (FR-004)
A1 | A | P1 | Preflight passes 6/6 | Mac on session network | Run scripts/preflight.sh | All 6 checks green; QR minted; onboarding URL printed | Mac
A2 | A | P1 | Cert SAN covers current IP | Network identity known | Preflight check 3 / cert-doctor.sh | Leaf cert SAN includes the Mac's current LAN IP | Mac
A3 | A | P1 | Root CA trusted on each tablet | CA installed once per device | Open https portal on tablet | Green lock, NO cert warning, getUserMedia allowed | iPad,Android
A4 | A | P2 | Onboarding page loads on a NEW tablet | Fresh tablet, CA not trusted | Scan QR → proceed → /onboard → install CA | Page renders; CA downloads + installs; lock turns green | iPad,Android
A5 | A | P1 | Travel-router (Beryl) full loop | Tablets on Beryl, MAC-privacy OFF | Run a full voice take over the kit LAN | Loop completes; NO new trust step (CA holds across networks) | iPad,Android
A6 | A | P2 | Mac IP stable across restart | Static DHCP lease bound | Restart router/Mac; recheck IP | Mac keeps the same IP; QR/cert still valid | Mac
B · Avatar tablet (FR-006)
B1 | B | P1 | Patient QR → 3D face loads | Patient persona, avatar mode | Scan patient QR | Translucent 3D face renders; no console errors | iPad
B2 | B | P1 | Lip-sync tracks speech | Avatar live | Trigger a spoken reply | Visemes track the audio; no desync | iPad
B3 | B | P2 | Emotion / altered-state reflected | Persona w/ emotion state | Drive a turn with emotion | Expression reflects the persona's state | iPad
B4 | B | P3 | Translucency slider works | Avatar live | Drag the slider | Opacity changes smoothly | iPad
B5 | B | P2 | Reconnect after network blip | Avatar live | Drop + restore Wi-Fi | WS reconnects; avatar resumes without reload | iPad
C · Audio station (FR-006b)
C1 | C | P1 | Audio QR → flat portrait (no 3D) | Non-patient, audio mode | Scan audio-mode QR | Flat portrait + name + badge; NO 3D rig | Android
C2 | C | P1 | Push-to-talk records | Audio station up | Hold, speak, release | Recording captured; transcription begins | Android
C3 | C | P1 | Room-local STT (Mac) transcribes | Portal up, STT warm | One spoken take | Transcript in ~1–2 s; character replies in voice | Android,Mac
C4 | C | P2 | Drug names transcribe correctly | Med board active | Say an order w/ a drug name | Drug name faithful (e.g. 'ceftriaxone') | Android,Mac
C5 | C | P3 | Name shows (not internal ID) | Bound character | Read the header | Persona name (e.g. 'Pharmacist Lee') | Android
C6 | C | P2 | On-device backup if portal drops | Portal unreachable | Take after drop | Names the failure + arms on-device fallback | Android
D · Voice loop end-to-end
D1 | D | P1 | Full loop PTT→STT→AI→TTS | Character bound, running | One complete take | Speech → transcript → character voice reply | iPad,Android
D2 | D | P1 | First words within target | Warm session | Time a reply | First audio ~2–3 s (streaming) | iPad,Android
D3 | D | P2 | iPad on-device STT (WebGPU) | iPad avatar | Take on iPad | On-device whisper (~1–1.5 s warm) | iPad
D4 | D | P2 | Several takes in a row | Warm session | 5 takes back-to-back | Consistent latency; no degradation | iPad,Android
E · Control room (FR-005)
E1 | E | P1 | Setup page renders all cards | Logged in, configured | Open /portal/control/setup | Med, devices, skins/voices, add-character present | Mac
E2 | E | P1 | START opens Live Ops window | On Setup | Press ▶ START | Goes live; Live Operations opens in a NEW window | Mac
E3 | E | P2 | Add character mid-session | Live session | Add a persona via banner | Character appears + becomes scannable | Mac
E4 | E | P2 | Avatar ⇄ audio toggle | Setup/Live | Flip a character's mode | QR re-mints for the chosen mode | Mac
E5 | E | P3 | Configured session lands on Setup | Configured | Navigate to /ops directly | Redirects to Setup | Mac
F · Say-as-character (FR-003)
F1 | F | P1 | Verbatim mode | Character bound | Say-as: verbatim line | Character speaks the exact text | iPad,Android
F2 | F | P1 | In-character mode | Character bound | Say-as: in-character intent | AI rephrases in persona voice/emotion | iPad,Android
G · Med ordering (FR-001/002)
G1 | G | P1 | Doctor orders decisively WITH dose | Doctor, condition set | Ask the doctor for orders | Doctor PLACES an order w/ a full dose; no 'what's available' | iPad,Android
G2 | G | P2 | Doctor escalates if already-on | Patient already on primary | Ask again | Doctor picks a different primary / escalates | iPad,Android
G3 | G | P1 | Instructor flags a med unavailable | Med board open | Toggle a med unavailable | Med marked unavailable in board state | Mac
G4 | G | P1 | Pharmacist coaches an alternative | Med flagged unavailable | Ask the pharmacist | Names an AUTHORED alternative (never invented) | Android
G5 | G | P2 | Doctor→pharmacist→doctor loop | Above set up | Run the loop | Doctor approves/adjusts w/ a dose | iPad,Android
G6 | G | P2 | Board condition matches the patient | Single + multi | Open the med board | Condition/formulary matches the PATIENT | Mac
H · Staged errors (FR-008)
H1 | H | P1 | Builder wizard flows end-to-end | Session running | Walk all 6 steps; pick a candidate | Next enables on selection; review; ARM works | Mac
H2 | H | P1 | Transcription (verbal) deliver→correct | Sound-alike armed (verbal) | Question, then read-back challenge | Doctor speaks wrong drug, defends, then CORRECTS + credits the catch | iPad,Android
H3 | H | P1 | Wrong dose (document) discrepancy | Armed wrong_dose·document·charting | Trainee reviews chart | Note contradicts the MAR; MAR stays correct (catchable) | iPad
H4 | H | P2 | Interaction error | Armed interaction | Run the encounter | Conflicting med vs an active med; pharmacist coaches | iPad,Android
H5 | H | P2 | Allergy oversight | Documented allergy present | Armed allergy | Allergy-conflicting med ordered despite the allergy | iPad,Android
H6 | H | P2 | Administration error | Armed admin·document | Trainee preps meds | MAR shows expired/wrong-time/look-alike deviation | iPad
H7 | H | P1 | Patient impact trigger + stabilize | Armed w/ impact | Trigger; then Stabilize | Patient symptomatic + vitals shift; Stabilize reverts both | iPad,Mac
H8 | H | P2 | Auto-trigger on administration | Impact = on_administer | Administer the staged med | Impact fires automatically | Android,Mac
H9 | H | P2 | Severe impact double-confirm | Severe impact armed | Press Trigger | Demands a second confirmation before firing | Mac
H10 | H | P1 | Caught / Missed marking | Error armed | Mark caught, then missed | Outcome recorded; transcript stamped | Mac
H11 | H | P1 | Debrief shows the full arc | Resolved error(s) | Open the debrief | Arc armed→delivered→impact→resolved + outcome (MISSED highlighted) [partial ✅] | Mac
H12 | H | P2 | Disarm restores chart byte-exact | Document error armed | Disarm it | Mutated chart artifact restored exactly | Mac
H13 | H | P1 | Multi-patient per-bed isolation | 2–3 bed room | Arm on bed A only | Bed A shows it; bed B unaffected; build scoped to bed | Mac
H14 | H | P3 | Builder opens in its own window | Setup/console | Click Build a staged error | Separate window; closing returns to the control panel | Mac
I · EHR / Medical Records
I1 | I | P1 | MR shows the correct PATIENT | Single + multi | Open the Medical Record | Chart is the PATIENT (never the doctor) | Mac
I2 | I | P2 | MR opens in its own window | Control panel | Launch EHR | Separate window; closing returns to an intact panel | Mac
I3 | I | P1 | Chart content correct | MR open | Inspect MAR/allergies/vitals/notes | All present + patient-correct | Mac
I4 | I | P2 | Order entry works | MR open | Place a lab/imaging/med order | Recorded + visible in chart/debrief | Mac
J · Multi-patient / room
J1 | J | P1 | Start a 2–3 bed room | Room wizard | Finalize a room | Each bed gets a join code + console | Mac
J2 | J | P1 | Per-bed roster + patient correct | Room running | Open each bed console | Correct patient + FULL roster checked (doctor/charge/RT/family) | Mac
J3 | J | P2 | Per-bed tools scoped | Room running | Use board/errors/devices on a bed | Each tool scopes to that bed only | Mac
J4 | J | P3 | Nursing station supervises beds | Room running | Open the nursing station | All beds' strips/transcripts visible | Mac
J5 | J | P2 | Transcripts land on the right bed | Multi-bed turns | Take on two beds | Each transcript lands on its own encounter | Mac,iPad,Android
K · Devices
K1 | K | P2 | Device join via QR | Device skin set | Scan a device QR | Device station joins + renders | iPad,Android
K2 | K | P3 | Pump program / alarm | Pump joined | Program a rate / alarm | Pump reflects program; alarm propagates | iPad
K3 | K | P2 | Med cart administer logged | Cabinet joined | Administer a med | 'RN administered …' logged to transcript | iPad,Mac
K4 | K | P2 | Telemetry + instructor override | Monitor up | Override a metric | Bedside monitor reflects the override | iPad,Mac
K5 | K | P2 | Scene inject | Live encounter | Inject vitals.drop / code.blue | Scene fires; vitals/alarms update | Mac
L · Debrief
L1 | L | P1 | Debrief builds after session | Session w/ activity | End session; open debrief | Renders w/ summary + transcript | Mac
L2 | L | P2 | Paired turns + tagging | Debrief open | Inspect transcript | Turns paired; NCJMM tagged | Mac
L3 | L | P1 | Staged-error arc section | Errors resolved | Inspect debrief | Full staged-error arc + outcomes | Mac
L4 | L | P3 | Documentation / orders alignment | Charting locked | Inspect debrief | Alignment cards populate | Mac
L5 | L | P2 | Per-patient debrief (multi) | Room session | Open each bed's debrief | Each patient's debrief separate + correct | Mac
M · Non-functional
M1 | M | P1 | Audio never leaves device/room | Any voice take | Confirm STT routing | On-device (iPad) or room Mac only; no third party | iPad,Android,Mac
M2 | M | P2 | Sustained 20-min session | iPad avatar | Run ~20 min continuous | No thermal throttle / latency creep | iPad
M3 | M | P2 | Reconnection after blip | Live session | Drop + restore network | Stations reconnect; session continues | iPad,Android
M4 | M | P3 | Device token enforcement (if on) | MEDSIM_FACE_TOKEN=1 | Hit /listen or /stt w/o token | 403 rejected | Mac
M5 | M | P1 | Restart behavior understood | Mid-session | Restart the portal | Known: session wiped → fresh Setup (FR-010 will improve) | Mac

## Issue Log
Issue ID | Test ID | Area | Severity | Title | Steps to reproduce | Expected | Actual | Environment (device/OS/browser/network) | Status | Date found | Resolution / commit
ISS-001 | H7 | Staged errors | Medium | (EXAMPLE) Stabilize left the symptom prompt active | Arm allergy error w/ moderate impact; Trigger; then Stabilize | Patient returns to baseline AND symptom prompt clears | Vitals reverted but the character mentioned itching one more turn | iPad Safari 26 / Beryl LAN | New | 2026-06-13

## Coverage
Area | Tests | Pass | Fail | Blocked | Not run | % pass
A · Network & pairing (FR-004)
B · Avatar tablet (FR-006)
C · Audio station (FR-006b)
D · Voice loop end-to-end
E · Control room (FR-005)
F · Say-as-character (FR-003)
G · Med ordering (FR-001/002)
H · Staged errors (FR-008)
I · EHR / Medical Records
J · Multi-patient / room
K · Devices
L · Debrief
M · Non-functional
TOTAL

## Environment
Device / role | Model | OS / browser | IP or join | CA trusted? | Private-MAC OFF? | Notes
Portal (Mac) |  | macOS | 192.168.x.x | n/a | n/a | run preflight.sh first
Avatar tablet | iPad | Safari 26
Audio station | Android | Chrome
Device station
Router | Beryl AX |  | 192.168.8.1 | n/a | n/a | bind Mac IP (static lease)