## How to use
MedSim VRAI — Validation Checklist
What this is | A SEQUENCED, do-it-during-the-session checklist for validating MedSim VRAI and for running a larger, multi-session field test. Companion to MedSimVRAI_Field-Test-Matrix.xlsx (that one is the broad 72-case COVERAGE map; this one is the actionable run-list + cohort log).
Order of work | 1) 'Session readiness' before every session. 2) Work the 'Validation drills' top to bottom (they build on each other). 3) 'Clinical review' is the instructor's sign-off on the DRAFT clinical data — do it once, re-check when data changes. 4) Log each session in 'Field-test sessions' to scale up.
Marking | Each drill row: set Result (Pass / Fail / Partial / Blocked / Not run / N-A), your initials, the date, and notes. A drill is 'done' only when its Expected column is observed.
Scaling to a larger field test | Run the same drills across cohorts/sessions; log each in 'Field-test sessions' (one row per session) for an at-a-glance rollup of how many sessions passed each feature. Add scenarios/cohorts as rows — the structure holds.
➜ Issues → Claude | When a drill fails, add a row to 'Issue log' (columns ordered for direct paste-to-Claude). Filter Status=New, copy rows incl. header, paste into Claude Code with 'Fix these field-test issues:'. Claude fixes + gates + replies with the commit; set Status Fixed → Verified after retest. (Same pipeline as the field-test matrix — keep ONE master issue log if you prefer.)
Field scripts | The staged-error and handoff drills mirror docs/FR-008-field-script.md and docs/FR-009-field-script.md — keep those open alongside.
Honest notes | Multi-patient handoff runs via the API (per-bed console UI is a follow-on). Handoff coverage scoring uses a deterministic heuristic with an AI-scorer hook (instructor override is the gate). Note these if a drill behaves accordingly.

## Session readiness
# | Readiness item | How / where | Result | By | Date | Notes
R1 | Pre-flight passes 6/6 | Run scripts/preflight.sh on the Mac
R2 | Mac IP + cert valid for THIS network | preflight check 3 / cert-doctor.sh — SAN covers the current IP
R3 | Root CA trusted on every tablet | Open the portal on each tablet → green lock, no warning
R4 | Private-MAC OFF on each tablet | iPad: Private Wi-Fi Address off · Android: use device MAC
R5 | Travel router (if used) — tablets joined | Beryl SSID; Mac IP bound (static lease)
R6 | AI + voice keys set | Anthropic + ElevenLabs keys configured in the portal
R7 | Room-STT warm (audio stations) | First take returns ~1–2 s; portal log shows model ready
R8 | Scenario configured + START | Setup: patient + characters chosen → ▶ START opens Live window
R9 | QR codes current | Fresh QR for the current network (preflight regenerates)

## Validation drills
# | Feature | Drill | Steps | Expected (what to verify) | Result | By | Date | Notes
Control room (FR-005)
C1 | Control room | Two-stage open | Setup → ▶ START | Scenario goes live; Live Operations opens in a NEW window
C2 | Control room | Add character + mode | Add a persona; flip avatar⇄audio | Character appears + scannable; QR re-mints for the chosen mode
Avatar / audio / voice
V1 | Avatar / audio / voice | Avatar loads + lip-sync | Scan a patient QR; trigger a reply | Translucent 3D face; visemes track the audio
V2 | Avatar / audio / voice | Audio station | Scan a non-patient (audio) QR; hold-to-talk | Flat portrait + name + badge (no 3D); PTT records
V3 | Avatar / audio / voice | Room-STT + drug names | One spoken order with a drug name | Transcript ~1–2 s; drug name faithful (e.g. 'ceftriaxone')
Med loop (FR-001/002)
M1 | Med loop | Doctor orders decisively | Ask the doctor for orders | Places an order WITH a dose; never asks 'what's available'
M2 | Med loop | Flag unavailable | Toggle a med unavailable in the board | Marked unavailable in board state
M3 | Med loop | Pharmacist alternative | Ask the pharmacist | Names an AUTHORED alternative (never invented)
M4 | Med loop | Loop closes | Back to the doctor | Doctor approves/adjusts with a dose
Staged errors (FR-008)
E1 | Staged errors | Sound-alike (verbal) | Arm transcription·verbal·med-pass; question then read-back | Doctor speaks wrong drug, defends once, CORRECTS when pressed + credits the catch
E2 | Staged errors | Wrong dose (document) | Arm wrong_dose·document·charting | A note contradicts the MAR; MAR stays correct (catchable)
E3 | Staged errors | Interaction | Arm interaction; run encounter | Conflicting med vs an active med; pharmacist coaches
E4 | Staged errors | Allergy + impact | Arm allergy w/ anaphylaxis impact (auto-on-administer); administer the staged med | Patient becomes symptomatic + vitals shift; Stabilize reverts both
E5 | Staged errors | Admin error | Arm admin·document·prep | MAR row shows expired/wrong-time/look-alike deviation
E6 | Staged errors | Severe double-confirm | Arm a SEVERE impact; press Trigger | Demands a second confirmation before firing
E7 | Staged errors | Caught/Missed → debrief | Mark caught + missed; open debrief | Debrief shows the full arc; MISSED highlighted (✅ already validated)
E8 | Staged errors | Multi-patient isolation | 2–3 bed room; arm on bed A only | Bed A shows it; bed B unaffected; builder scoped to the bed
Shift handoff (FR-009)
H1 | Shift handoff | Off-going: probe gaps | Handoff card → offgoing → give report omitting allergy/watch-fors | AI nurse probes the HIGH-RISK gaps + asks for a read-back
H2 | Shift handoff | Off-going: survey + score | Tablet &survey=1 (answer by voice) → Score | Coverage map; Self% vs measured% → OVERESTIMATE when over-rated; blind-spot flagged
H3 | Shift handoff | Off-going: confirm + debrief | Tick/override coverage lines; Open debrief | Only confirmed lines render; debrief 'Shift handoff' section populated
H4 | Shift handoff | Oncoming: receive + read-back | oncoming · typical_gaps; student asks + summarizes | AI gives report under-covering gaps; receiver metrics show questions + synthesis
H5 | Shift handoff | Oncoming: staged-error embedded | Arm a report-encounter error; dial=staged_error | Survey 'did anything not match?' probes the catch; discrepancy CAUGHT/MISSED in debrief
H6 | Shift handoff | Multi-patient prioritization | Charge-nurse turnover (≥2 patients, via API) | After the last patient, AI asks 'who first + why'; expected_priority ranks unstable→stable
Non-functional
N1 | Non-functional | Audio stays in-room | Confirm STT routing | On-device (iPad) or room Mac only; no third party (cloud off)
N2 | Non-functional | Restart behavior | Restart the portal mid-session | Known: session wiped → fresh Setup (FR-010 will improve)

## Clinical review
# | Item to review (instructor / clinical SME) | Where | Verdict | By | Date | Notes
CR1 | Medication orders — conditions, primaries, alternatives, min-doses clinically sound | portal/data/med_orders.json (26 conditions, DRAFT)
CR2 | Sound-alike pairs appropriate for learners | med_errors.json · sound_alike_pairs
CR3 | Dose-error transforms realistic (10x, mg↔mcg, double/half) | med_errors.json · dose_transforms
CR4 | Interaction pairs + risk labels correct | med_errors.json · interaction_pairs
CR5 | Allergy → med map (incl. cross-reactivity teaching point) | med_errors.json · allergy_map
CR6 | Admin-error templates plausible | med_errors.json · admin_error_templates
CR7 | Consequence profiles × tiers — symptoms + staged vitals clinically plausible | med_errors.json · impacts (8 profiles × mild/moderate/severe)
CR8 | Handoff element checklist + high-risk list right for your program | FR-009 strategy PDF · §4.1 / docs
CR9 | Handoff survey questions appropriate | FR-009 strategy PDF · §4.4

## Field-test sessions
Session # | Date | Facilitator | Cohort / group | # students | Scenarios run | Features exercised | Drills passed / total | Issues found | Overall verdict | Notes
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20

## Issue log
Issue ID | Drill / Test ID | Feature | Severity | Title | Steps to reproduce | Expected | Actual | Environment (device/OS/browser/network) | Status | Date found | Resolution / commit
ISS-001 | H2 | Shift handoff | Medium | (EXAMPLE) Coverage marked 'pending' as said when it wasn't | Off-going drill; student never mentioned pending labs; Score | Pending shows ✗ (missed) | Pending shows ✓ — heuristic matched 'result' in an unrelated sentence | iPad Safari 26 / Beryl LAN | New